## Pre-estimate checklist (hidden)
Pre-estimate checklist:
Project Process | Yes | No | not necessary
Requirements
Are the Project Requirements clearly documented and Understood? (by both I.S. and the Client?) |  | X
Is the criteria for meeting each requirement defined? |  | X
Are the Project Requirements Baselined (Under change control)? |  | X
Is there a "Client approved" plan for Requirements changes? |  | X
Has a Requirements Traceability Matrix been developed? |  | X
Have the requirements been validated against the business objectives? |  | X
Have you considered all of the processes that must be followed during the project life cycle? |  | X
Have you considered all of the interfaces that must be adhered to? |  | X
Scoping
Has a Statement of Work (SOW) been reviewed/approved by the Client |  | X
Has the Statement of Work been reviewed by the virtual team partners? |  | X
Has a Work Breakdown Structure (WBS) been reviewed by the Client |  | X
Has the WBS been reviewed by the virtual team partners? |  | X
Risk
Has a formal Risk Assessment been done? (including probability, impacts, avoidance & recovery) |  | X
Is there an approved Risk Management Plan? |  | X
Was a Client representative involved with the Risk Management Plan? |  | X
Were appropriate I.S. resources involved in the Risk Management Plan? |  | X
Environments
Is the process for identifying, acquiring, establishing, and verifying the environment understood and included in the plans for the project?
Is the Development environment adequate to support the project?
Is the Operational environment adequate to support the project?
Staff
Are appropriate staff available for the project?
Are the resources committed to participate in the required activities?
Is there a training plan to cover deficiencies?
Total for Blank | 22 | 6 | 22
Total non blank | 0 | 16 | 0
100%
Anything more than 0% is alarming and preventing action needs to be taken to mitigate the risk
Anything above 50% in non acceptable zone and should go into no-go, unless strategically decided to go for.
Colour code o% - Green, 0 to 50% - yellow and above 50% red.

## Effort
Organisation Estimation Sheet
Project Code: |  |  |  | Client Name:
Project Name: |  |  |  | Ver No.
Project Manager: |  |  |  | Date:
Estimator: |  |  |  | Reviewer:
Complexity Table |  |  |  | Factor Applicable for this Application based on Team Skill Level
Set Productivity
1 IP equals | 0.8 |  | PD | [5 empty] | effort = size / PD
Set Complexity |  |  |  | Low |  |  | 1.1 |  | 0.625
Comp. Type | Complexity Factor |  |  | Medium | Medium |  | 1
Very simple | 0.5 | IP | 0.625 | High |  |  | 0.9
Simple | 1 | IP | 1.25 |  |  |  |  | VS | L
Medium | 2 | IP | 2.5 | Legend |  |  |  | S | M
Complex | 4 | IP | 5 | Editable Field |  |  |  | M | H
Very complex | 6 | IP | 7.5 | Not to be edited Field |  |  |  | C
VC
WBS No. | Work Breakdown Structure (WBS) |  |  |  |  | Complexity | Effort based on Complexity | Skill | Effort based on Complexity and Skill
1 | [6 empty] | 0 | H | 0
2 | [6 empty] | 0
3 | [6 empty] | 0
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0
18 | [6 empty] | 0
19 | [6 empty] | 0
20 | [6 empty] | 0
21 | [6 empty] | 0
22 | [6 empty] | 0
23 | [6 empty] | 0
24 | [6 empty] | 0
25 | [6 empty] | 0
26 | [6 empty] | 0 | H | 0
27 | [6 empty] | 0 | H | 0
28 | [6 empty] | 0 | H | 0
29 | [6 empty] | 0 | H | 0
30 | [6 empty] | 0 | H | 0
31 | [6 empty] | 0 | H | 0
32 | [6 empty] | 0 | H | 0
33 | [6 empty] | 0 | H | 0
34 | [6 empty] | 0 | H | 0
35 | [6 empty] | 0 | H | 0
36 | [6 empty] | 0 | H | 0
37 | [6 empty] | 0 |  | 0
38 | [6 empty] | 0 |  | 0
39 | [6 empty] | 0 |  | 0
40 | [6 empty] | 0 |  | 0
41 | [6 empty] | 0 |  | 0
42 | [6 empty] | 0 |  | 0
43 | [6 empty] | 0 |  | 0
44 | [6 empty] | 0 |  | 0
45 | [6 empty] | 0 |  | 0
46 | [6 empty] | 0 |  | 0
47 | [6 empty] | 0 |  | 0
48 | [6 empty] | 0 |  | 0
49 | [6 empty] | 0 |  | 0
50 | [6 empty] | 0 |  | 0
51 | [6 empty] | 0 |  | 0
52 | [6 empty] | 0 |  | 0
53 | [6 empty] | 0 |  | 0
54 | [6 empty] | 0 |  | 0
55 | [6 empty] | 0 |  | 0
56 | [6 empty] | 0 |  | 0
57 | [6 empty] | 0 |  | 0
58 | [6 empty] | 0 |  | 0
59 | [6 empty] | 0 |  | 0
60 | [6 empty] | 0 |  | 0
61 | [6 empty] | 0 |  | 0
62 | [6 empty] | 0 |  | 0
63 | [6 empty] | 0 |  | 0
64 | [6 empty] | 0
65 | [6 empty] | 0
66 | [6 empty] | 0
67 | [6 empty] | 0
68 | [6 empty] | 0
69 | [6 empty] | 0
70 | [6 empty] | 0
71 | [6 empty] | 0
72 | [6 empty] | 0
73 | [6 empty] | 0
74 | [6 empty] | 0
75 | [6 empty] | 0
76 | [6 empty] | 0
77 | [6 empty] | 0
78 | [6 empty] | 0
79 | [6 empty] | 0
80 | [6 empty] | 0
81 | [6 empty] | 0
82 | [6 empty] | 0
83 | [6 empty] | 0
84 | [6 empty] | 0
85 | [6 empty] | 0
86 | [6 empty] | 0
87 | [6 empty] | 0
88 | [6 empty] | 0
89 | [6 empty] | 0
90 | [6 empty] | 0
91 | [6 empty] | 0
92 | [6 empty] | 0
93 | [6 empty] | 0
94 | [6 empty] | 0
95 | [6 empty] | 0
96 | [6 empty] | 0
97 | [6 empty] | 0
98 | [6 empty] | 0
99 | [6 empty] | 0
100 | [6 empty] | 0
101 | [6 empty] | 0
102 | [6 empty] | 0
0
0
0
0
0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[6 empty] | Total Effort | 0 |  | 0
[6 empty] | Skill Level | 0.9
[6 empty] | Final Effort in MD | 0 |  |  | 3
[6 empty] | Final Effort in Hours | 0
[6 empty] | Size | 0
Note on B12: Rahul Raj: Index Productivity
Note on E12: Rahul: Person Days
Note on J22: Total efforts required for Coding and Unit Testing (includes Peer Reviews etc.) of the Module / Component THE EFFORT IS ONLY FOR CODING AND UNIT TESTING and nothing more.
Note on L22: Total efforts required for Coding and Unit Testing (includes Peer Reviews etc.) of the Module / Component THE EFFORT IS ONLY FOR CODING AND UNIT TESTING and nothing more.

## Effort Distribution
Organisation Estimation Sheet
0
Project Code: | 0 |  | Client Name: |  | 0
Project Name: | 0 |  | Ver No. |  | 0
Project Manager: | 0 |  | Date: |  | 0
Estimator: | 0 |  | Reviewer: |  | 0
Effort Distribution
SDLC Phases |  | % age Disribution | Computed Effort (Hours) | Proposed Effort (PD) | Rationale For Change
Requirement Analysis |  | 10% | 0
Design |  | 5% | 0
Coding and Unit Testing (CUT) |  | 48% | 0
System Testing |  | 15% | 0
|  | 0% | 0
Deployment & UAT Support |  | 2% | 0
Total SDLC Effort |  | 80% | 0 | 0
Non-SDLC Phases |  | % age Disribution | Effort (Hours)
Technical Documentation Includes test plan, test case preperation, Release Note |  | 4% | 0
Configuration Management (IT Infra, Trg, supp) |  | 3% | 0
Project Management |  | 10% | 0
Review ( Code and document review ) |  | 3% | 0
Total Non-SDLC Effort |  | 20% | 0
Total Project Effort (Computed) |  |  | 0
Total Project Effort (Proposed) |  |  | 0

## Final Summary
Organisation Estimation Sheet
0
Project Code: | 0 | Client Name: |  | 0
Project Name: | 0 | Ver No. |  | 0
Project Manager: | 0 | Date: |  | 0
Estimator: | 0 | Reviewer: |  | 0
Summary
Total Points |  |  | 0
Total Effort in Person Days (Computed effort) |  |  | 0
Total Effort in Person Days (Proposed effort) |  |  | 0
Productivity Assumed (Initially) |  |  | 0.8
Assumptions Made During Estimation
1
2
3
4
5
6
7
8
9
Risks Identified During Estimation
1
2
3
4
5
6
7
8
9

## Guidelines
Organisation Estimation Sheet
The guidelines for assigning Complexities to projects
Very simple | Simple | Medium | Complex | Very Complex
induction of a reusable code with known features | Modification in forms | addition of services/reports | Addition of data base table / filed | additon of integration, or new feature of integration through new middleware
1. <=1Validations or 2. No Business Rules Or 3. No Calculations Or 4. No of Fields<=8 and 5. No Tabbed design | 1.Validation Checks <=3 Or 2. Simple calculations that are addition, subtraction, multiplication and division. Or 3. No. of Fields <=9 and =>20 and 4. No Tabbed Design | 1. Validation of Business rules>3 but less than 10 OR 2. Complex Calculations/Derivations OR 3. No. of Fields >20 but less than 40 OR 4. Upto 3 Tab on the same Screen | 1. Any derived calculations 2. No of input and output Fields >30 | 1. No of fileds >40 Or 2. Number of subgroups within the logical data files >4
1. No Calculations Or 2. No. of input and output fields <=10 | 1. Simple calculations that are addition, subtraction, multiplication and division. Or 2. No. of input and output fields =>10 and <=20 | 1. Any derived calculations 2. No of input and output Fields>20 and <=30 | 1. Validation of Business rules>10 OR 2. Complex Calculations/Derivations/On Screen auto calculation OR 3. No. of Fields > 30 OR 4. More than 3 tab on the Screen | 1. Multiple data files or web services interfaced. 2. Multiple use of data files or web service, API and Third party tool like Paymeny Gateway
1. Simple Query Processing Or 2. No Change / modification on data. | More than one but less than three external data files or web service interfaced. | Multiple data files or web services interfaced
1. No of fileds <=10 Or 2. Number of subgroups within the logical data files is equal to 1 | 1. No of fileds >10 and <=20 Or 2. Number of subgroups within the logical data files <=2 | 1. No of fileds >20 and less <=30 Or 2. Number of subgroups within the logical data files >2 and <4