## Title
Logs
Project Manager | Vishal Kumar Soni
Date | 2015-06-11
Client Name
Project Name | Revive Redesign
Note on B4: Please enter the name of project manager.
Note on B7: This is a derived field and displays today's date.
Note on B9: Enter the client's name.
Note on B11: Please enter the project name. This field is used in the other worksheets, i.e. chg-req, config, risks and out-items.

## chg-req
REQUEST FOR CHANGE LOG
Project Name
Revive Redesign
No. | Brief Description | Requested | Requested | Priority | Status | Status | Resource | Compl. | Total Work | Total
|  | by | Date | Level |  | Date | Type | (Y/N) | (p/days) | Cost ($)
CR001 | New functionality to add Manufacturer., Change in Add/Edit users to add,Functionality to Manage Manufacturer,creating ,Manufacturers should be able to see orders ,) All repots which are related to manufacturer should show records which are related to manufacturer | Reuben | 06/11/2015 | (MAN)datory | (APP)roved |  | (MAT)erial | N | 25
CR002 | Add invoice field(alpha numeric), Add same column in machine activity report , System should send information of logged,Add new attribute of “Eligibility Wait Period, Update business rules, Add different modes in to the system as “Manufacturing” , “Debug” , “Live”, “Training”, “Demo”. fo | Reuben | 2015-06-11 | (MAN)datory | (APP)roved |  | (MAT)erial | N | 31
CR003 | New report needed: "Reconciliation" - Filters: customer, location, start date, end date; results: customer, location, start time and date, end time and date, invoice #, success/failure, member/non-member, user id.,Delete Membership functionality, Delete Location functionality on ES. | Reuben | 2015-09-10 | (MAN)datory | (APP)roved |  | (MAT)erial | N | 5
CR004 | Machine search result should be passworded, Remove “Renew and Edit” buttons , Change Search button , The search criteria pages should be the, Add last dry attempt | Reuben | 2015-09-22 | (MAN)datory | (APP)roved |  | (MAT)erial | N | 4
CR005 | ) New Report Report Name: Machines – Unassigned Report Details: List of machines not assigned to a location Filters: Manufacturer (Not a required Field), Order # (Not a required Field) Report Fields: Order #, Manufacturer, Machine ID 2) Admin screen | Reuben | 2015-09-22 |  | Approval (PEN)ding |  | (MAT)erial | N | 5
CR006 | Fault handling as per attached document | Reuben | 2015-11-05 | (MAN)datory | (APP)roved |  | (MAT)erial | N | 17
CR007 | Admin and Super admin should have rights to approve the machine orders | Reuben | 2015-12-22 |  | Approval (PEN)ding |  | (MAT)erial | N | 32
CR008 | Import functionality to import the store users | Reuben | 2016-01-12 | (MAN)datory | (APP)roved |  | (MAT)erial | N | 3
CR09 | Implement the functionality of corporate/sub agent level. For detailed requirement please refer to document “Redux-Subsidiary Functionality” | Reuben | 2016-01-25 | (MAN)datory | (APP)roved |  | (MAT)erial | N | 30
CR0010 | Importing current memberships into system. | Reuben | 2016-02-02 |  | Approval (PEN)ding |  | (MAT)erial | N | 8
CR0011 | create three new API,add new ManufacturerID,add new web API order ID, add Machine ID | Reuben | 2016-02-10 | (MAN)datory | (APP)roved |  | (MAT)erial | N | 5.5
|  |  |  | Priority: |  | Status: |  | Resource Type;
|  |  |  | (MAN)datory |  | Approval (PEN)ding |  | (MAT)erial
|  |  |  | (NEC)essary |  | (APP)roved |  | (HR) Human Resource
|  |  |  | (DES)irable |  | (CAN)celled
(DEF)erred
Note on A2: This field is replaced by the Project Name entered in the Title worksheet.
Note on A4: Enter the change request number from the Request for Change form.
Note on B4: Enter the same description as the Brief Description in the Request for Change form.
Note on D4: Enter the same information as in the Requested by field in the Request for Change form.
Note on E4: Enter the same information as was checked in the Priority Level field in the Request for Change form. Values for this field are: (MAN)datory, (NEC)essary, (DES)irable.
Note on F4: This is the status of the Request for Change. It corresponds to the Client Decision on the Request for Change form. Values for the status are: . Approval (PEN)ding, . (APP)roved, . (CAN)celled, .(DEF)erred.
Note on G4: This is the Date entered in the Client Decision field in the Request for Change form.
Note on H4: Rahul: Enter the type of resource required to perform the Request for Change, i.e. (MAT)erial or (HR) human resource
Note on I4: Enter (Y) yes if the work has been completed or (N) no if the work has not been completed.
Note on J4: Enter the same information as entered in the TOTAL Work field on the Request for Change form.
Note on K4: Enter the same information as entered in the TOTAL Cost ($) field on the Request for Change form.