## Instructions
Instructional Notes for the RACI Matrix:
The RACI Matrix is a powerful tool to assist in the identification of roles and assigning of cross-functional responsibilities to a project deliverable or activity. RACI represents: R - Responsibility, A - Accountable, C - Consulted, and I - Informed RACI Definitions: Responsibility = person or role responsible for ensuring that the item is completed Accountable = person or role responsible for actually doing or completing the item Consulted = person or role whose subject matter expertise is required in order to complete the item Informed = person or role that needs to be kept informed of the status of item completion
Simply place an R, A, C, I or any appropriate combination in each of the applicable roles for each activity Each Activity should have at least one individual Accountable while there may be shared responsibilities depending on the activity.

## RACI Matrix
RACI Matrix | Project Name
| OnSite Project Manager | Off Shore Project Manager | Develivery Head | Requirement Analyst | Technical Architect/TL/ DB Design | Lead Developer | Developer | QC Lead/QA | Tester | Infrastructure | Configuration Manager
Initiate Phase Activities
INI - Kick Off | I | R | A | I | C | I | I | I | I | I | I
INI - Prepare PMP | C | R | A | I | I | I | I | I | I | I | I
INI - Approve PMP | C | R | A | I | I | I | I | I | I | I | I
Plan Phase Activities
REQ - SRS Prepare | C | A | I | R | C | I | I | I | I |  | I
REQ - SRS Review | C | R | A | C | C | I | I
REQ - SRS Approve | A | R | C | C | C | I | I | I | I | I | I
Design Phase Activities
DES - Design Prepare | I | A | C | I | R | I | I | I | I
DES - Design Review | I | R | C | I | A | I | I | I | I
Coding Phase Activities
COD - Coding |  | C |  |  | I | A | R | I | I
COD - Code Review | A R: A; I I: R; I I: C; I I: I
COD - Unit Testing | A R: I; R A: I; I I: A; I I: R
Testing Phase Activities
TES - Test Plan |  | A | I | I | I | I | I | R | I
TES - Test Strategy |  | A | I | I | I | I | I | R
TES - Test Case |  | C |  | I | I | I | I | A | R
TES - RTM |  | C |  |  | I | I | I | A | R
TES - Testing |  | C | I |  | I | I | I | A | R
TES - Bug Fixing |  | C | I |  | I | I | R | A | C
TES - Verification |  | C | I |  | I | I | C | A | R
Release Phase Activities
REL - Release Notes | C | R | A | I |  | I | I | C | I
REL - Deployment/Installation | C | R | A | I | I | I | I | I | I
Close Phase Activities
CLO - Complete Project Closure | C | R | A | I | I | I |  | I
Configuration Management
CON - Configuration Management Plan |  | R |  |  | C | C | I | I | I |  | A
Quality Assurance Activities
QA - Internal Auditing |  | A | I | I | C | I | I | R | I
Human Resource Activities
HUM - Training |  | A: R; I: A; C: I
Infrastructure Activities
INF - Infrastructure Redines | [9 empty] | R | bar: A to I; C
R
A
C
I
I/C
Note on C186: Rahul:
Role
Role
Project Deliverable (or Activity)

## Sheet2
| Project Sponsor | Project Director | Project Manager | Project Team | Steering Committee
Project Charter | A | A | R | C | A
Communication Management Plan | A | C | R | I | C
Business Requirements | A | I | R | C | I
Status Reports | I | I | R | C | I