## Defect Report
P1
P2
[15 empty] | P3 | New
|  | Defect Report Summary | [12 empty] | P4 | Open
[15 empty] | P5 | Assigned
|  | Project Name | <Enter Project Name |  |  | Project Id | [9 empty] | Re-Assigned
Fixed
Reject
SL No | Defect ID | Module | Defect Description | Lifecycle Phase/ RCA | RCA Description | Defect Raised By | Defect Raised On | Status | Priority | Assign To | Defect Closed On | Defect Open Age | Remarks | Attachment |  | Re-Test
1 | Bug id 4781 | Job Order | Artcore Issues reported as of 22 oct 2012 | Requirement |  | Client | 2012-11-09 | Fixed | P1 | Akshay | 2012-11-10 | 1 |  |  | Open
2 | Bug id 4782 | Job Order | Manage customer search Issue | Enhancement | Usability | Client | 2012-11-09 | Fixed | P1 | Akshay | 2012-11-10 | 1 |  |  | New
3 | Bug id 4783 | Job Order | Random Issue - IN Job Order pICKUP AND DELIVERY INFORMATION losing information | Design | Understanding gap by client | Client | 2012-10-22 | Fixed | P1 | Akshay | 2012-11-10 | 19 |  |  | Fixed
4 | Bug id 4620 | Site Admin/ Operations | Alphabetize |  |  | Client | 2012-05-09 | Fixed | P1 | Rajeev | 2012-11-10 | 185 | Enhancement |  | Closed | Closed
5 | Bug id 4320 | Job Order | Job Order summary activity details |  |  | Client | 2012-04-27 | Fixed | P1 | Rajeev | 2012-11-10 | 197 | CR |  | Reopened | Re-Open
6 | Bug id 4645 | Site Admin/ Operations | Auto Scan |  |  | Client | 2012-05-09 | Fixed | P1 | Rajeev | 2012-11-10 | 185 | Critical |  | Rejected | Deferred
7 | Bug id 4646 | Site Admin/ Operations | Contacts |  |  | Client | 2012-08-07 | Fixed | P1 | Rajeev | 2012-11-10 | 95 | Critical but its a business logic. |  | Deffered
8 | Bug id 4274 | Site Admin/ Operations | Users |  |  | Client | 2012-04-05 | Fixed | P1 | Rajeev | 2012-04-10 | 5 | Normal |  | WontFix
9 | Bug id 4299 | Site Admin/ Operations | session expires when actively working on database |  |  | Client | 2012-04-13 | Fixed | P1 | Rajeev | 2012-05-10 | 27 | Normal |  | Duplicate
10 | Bug id 4314 | Operations | Master Data: Customer & Location |  |  | Client | 2012-04-13 | Fixed | P1 | Rajeev | 2012-05-10 | 27 | Major |  | Invalid
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Requirement
Design
Code
Testing
Deployment
UAT
CR
Enhancement

## DRE-DDD
D. DEFECTS
D.1 % of DDD ( Delivered Defect Density in the reporting period) | [7 empty] | D.2 % DRE (Defect Removal Effectiveness for the Reporting Period)
Formula: | (Customer Reported Defects / Delivered Size) | [6 empty] | Formula: | (Internal QC Defects / (Internal + Customer Reported Defects))*100
Frequency: | Project Closure/ Periodically | [6 empty] | Frequency: | Periodically
Unit: | number | [6 empty] | Unit: | %
Goal | 0.2 | [6 empty] | Goal: | 80
| Project A | Project A | Project B | Project C | Project D | Project E | Project F |  | Project A | Project A | Project B | Project C | Project D | Project E | Project F
Customer Reported | 3 | 2 | 0 | 0 | 0 | 0 | 1 | Internal Defects | 51 | 42 | 86 | 211 | 316 | 297 | 14
Delivered Size | 70 |  | 80 | 137.58 | 80 | 100 | 120 | Client Defects | 3 | 0 | 4 | 3 |  | 2 | 1
DDD | 0.042857 |  | 0 | 0 | 0 | 0 | 0.0083333 | Total Defects | 54 | 42 |  | 214 | 316 | 299
[8 empty] | DRE | 94.4444 | 100 | 95.5556 | 98.5981 | 100 | 99.3311 | 93.3333
93
Note:- All the defects are logged in TFS

## Defect Report Summary
| Lifecycle Phase | (All)
Module/Sub Module/Screen/ Functionality Name | Count of Status | Column Labels
Create Job Order |  | Fixed | (blank) | Open | Assigned | Grand Total
Create Storage Accounts | Row Labels |  | (blank) | P1 | P1
Issues raised by kavitha | Job Order | 2 |  | 1 | 1 | 4
Login | Operations | 1 |  |  |  | 1
Logout | Site Admin/ Operations | 3 |  | 1 | 1 | 5
Manage Art Handlers | (blank)
Manage Customers | Grand Total | 6 |  | 2 | 2 | 10
Manage Job Order
Manage schedule
Manage Storage Accounts
Manage Trucks
Menu Mapping
MOM from Artcore demo
Schedule
Storage Accounts
UAT-Artcore
UAT-Job Order
UAT-Master Data
UAT-Schedules
UAT-Session Expire
UAT-Storage
UAT-User Mapping
User Level Management
User Management
(blank)
Grand Total

## RCAINS
RCA | Requirement | Design | Code | Testing | Enhancement | Deployment | UAT | Change_Request | CR_Bug
RCA Dec | Requirement not clear | Compatibility Issue | Requirement Not Implemented | Environmental Issue | Requirement Missing | Environmental Issue | Change Request | New Requirement | Imapct Analysis
| Requitrement GAP | UI Design Issue | Partial Implemented | Compatibility Issue | Usability | Configuration Issue | Configuration Issue | Change in existing requiremnet | Requirement not clear
|  |  | Syntax Error | Integration Issue | New Functionality | Data Migration Issue | Data issue | requirement not clear to client | Environmental Issue
|  |  | Data Error | Out of Scope |  | Partial Deployed | Data Migration Issue |  | Configuration Issue
|  |  | Logic Error | Requirement Not clear |  |  | Enhancement |  | Missed during Internal Testing
|  |  | Business Rule | Impact Analysis of CR |  |  | Environmental Issue
|  |  | Missing Function | Testing miss |  |  | Functional Issue
Missed during Internal Testing
Partial Deployed
Performance Issue
Requirment not gathered or not elaborated in SRS
Security Issue
| Name | Range Address |  |  |  |  | UI Issue
| Requirement | B2:B13 |  |  |  |  | Understanding gap by client
| Design | C2:C13 |  |  |  |  | Usability Issue
| Code | D2:D13
| Testing | E2:E13
| Enhancement | F2:F13
| Deployment | G2:G13
| UAT | H2:H13
| Change_Request | I2:I13
| CR_Bug | J2:J13