## Summary Sheet
Metrics Report # <Project Name>
S.No | Metrics | Goals as per Metrics Report # | Current Goals as per Metrics Report # | Unit | Remarks
1 | Schedule Variance till the milestone with respect to initially planned schedule (For development projects only) | 15 |  | %
2 | Schedule Variance for CR | 15 |  | %
3 | EV for the Project wrt Initially Planned Effort | 10 |  | %
4 | Effort variance for the CRs | 10 |  | %
5 | DDD (Delivered Defect Density) | 0.2 |  | Number
9 | % of Defects in Coding till the reporting period | NA |  | %
10 | % of Defects reported by Client/onsite team, till the reporting period | 10 |  | %
6 | DRE (Defect Removal Effectiveness) | 80 |  | %
12 | Avg. age of open CRs | NA | NA | Days | Depends on the type of CR
13 | Avg. age of closed CRs | NA | NA | Days | Depends on the type of CR
14 | FM - Mean Time to Resolve a problem | 5 | 5 | Hours
The delivered Size will be calculated from the total of function point for developed software and CR and No. of Enhamcement received from customer.Enhancement is calaculated as 2 point/enhancement.

## SV & Delivery
A. SCHEDULE VARIANCE
A.1 Schedule Variance till the Project End with respect to initially planned schedule
(For development projects only)
Formula: | (Actual end date of the milestone – Initially planned end date of the milestone) / (Initial planned end date of the milestone – initial planned start date of the project)) *100
Frequency: | Phase End
Unit: | %
Goal | +15
| Phase1 | CR
SV (%)
Actual End Date
Initially Planned End Date
Initial Planned Start Date
Note on B10: Rahul: (30Oct-30 oct12)-(30 oct12-9Aug12)*100 0/59*100=0%
Note on C10: Rahul: (28jan13-25jan13)/(25jan13-16jan13)*100 (3/7)*100=42.85

## EV
C. EFFORT VARIANCE
C.1 Effort variance for the project with respect to initially planned effort
Formula: | ((Actual effort in the project– initially planned effort for the project) / initially planned effort for the project) *100
Frequency: | Project Closure
Unit: | %
Goal: | +-10
|  | Phase 1 | CR
Planned Effort (Hours)
Actual Effort (Hours)
| EV(%) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
C.2 Effort variance for the project with respect to initially planned effort for Phase 1 only
Formula: | ((Actual effort in the project– initially planned effort for the project) / initially planned effort for the project) *100
Frequency: | Project Closure
Unit: | %
Goal: | +-10
|  | RA | Design | Coding | Testing | CM | QA | PMC | RD
Planned Effort (Hours)
Actual Effort (Hours)
| EV(%) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Note on K12: Rahul: include start date & End Date

## Defects
D. DEFECTS
D.1 % of DDD ( Delivered Defect Density in the reporting period) |  |  |  | D.2 % DRE (Defect Removal Effectiveness for the Reporting Period)
Formula: | (Customer Reported Defects / Delivered Size) |  |  | Formula: | (Internal QC Defects / (Internal + Customer Reported Defects))*100
Frequency: | Project Closure/ Periodically |  |  | Frequency: | Periodically
Unit: | number |  |  | Unit: | %
Goal | 0.2 |  |  | Goal: | 80
| Phase 1 | Softheon | CR |  | Phase 1 | CR
Customer Reported |  |  |  | Internal Defects
Delivered Size |  |  |  | Client Defects
DDD | #DIV/0! |  | #DIV/0! | Total Defects
|  |  |  | DRE | #DIV/0! | #DIV/0!
Note on B11: Rahul: Function Point for CR & Enhancement
Note on D11: Rahul: Function Point for CR & Enhancement
Note on B13: Rahul: Total Function point is 24 + total ehhancement point (13*2=26)=24+26
Note on I14: Rahul: (Internal + Customer Reported Defects)