## Summary Sheet
Metrics Report #
S.No | Metrics | Goals as per Metrics Report # | Current Goals as per Metrics Report # | Unit | Remarks
1 | Schedule Variance till the milestone with respect to initially planned schedule (For development projects only) | 15 |  | %
2 | EV for the Project wrt Initially Planned Effort (For Development Projects) | 10 |  | %
3 | Effort variance for the CRs (or Enhancement Request) closed during the reporting period | 10 |  | %
4 | Number of defect delivered density in application till the reporting period | 0.2 |  | Number
9 | % of Defects in Coding till the reporting period | NA |  | %
10 | % of Defects reported by Client/onsite team, till the reporting period | 10 |  | %
5 | DRE (Defect Removal Effectiveness) | 80 |  | %
6 | Project Effort Distribution | NA |  | %
12 | Avg. age of open CRs | NA |  | Days | Depends on the type of CR
13 | Avg. age of closed CRs | NA |  | Days | Depends on the type of CR
14 | FM - Mean Time to Resolve a problem | 5 |  | Hours
8 | Average Training Days/emplyee/quarter | 1 manday / training / quarter |  | Days
9 | Average Customer Satisfaction Index | 80 |  | %

## Project Data Table
PROJECT DATA TABLE
Ongoing Projects |  | Closed Projects |  | Not Approved
Projects | Actual End Date/Till Date, if project / phase is ongoing | Initial Planned Start Date | Initial Planned End Date | Latest Planned Revised Start Date | Current Phase | Total Efforts till Date (hours)
Softheon
Project Name 1
Project Name 2
Project Name 3
Project Name 4
Project Name 5

## SV
A. SCHEDULE VARIANCE
A.1 Schedule Variance till the Project End with respect to initially planned schedule
(For development projects only)
Formula: | (Actual end date of the milestone – Initially planned end date of the milestone) / (Initial planned end date of the milestone – initial planned start date of the project)) *100
Frequency: | Phase End
Unit: | %
Goal | +15
| Project 1 | Project 2 | Project 3 | Project 4 | Project 5
SV (%)
Actual End Date
Initially Planned End Date
Initial Planned Start Date

## EV
C. EFFORT VARIANCE
C.1 Effort variance for the project with respect to initially planned effort
Formula: | ((Actual effort in the project– initially planned effort for the project) / initially planned effort for the project) *100
Frequency: | Project Closure
Unit: | %
Goal: | +-10
|  | Project 1 | Project 2 | Project 3 | Project 4 | Project 5
Planned Effort (Hours)
Actual Effort (Hours)
| EV(%) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## Defects
D. DEFECTS |  |  |  |  | Calculated on dummy data
D.1 % of DDD ( Delivered Defect Density in the reporting period) | [7 empty] | D.2 % of defects in coding(Defects in coding refer to defects found during testing )
Formula: | (Customer Reported Defects / Delivered Size) | [6 empty] | Formula:
Frequency: | Project Closure/ Periodically | [6 empty] | Frequency: | Project Closure/ Periodically
Unit: | Numer | [6 empty] | Unit: | %
Condition: | No Defect log has been logged for Palmbay Project | [6 empty] | Condition: | No Defect log has been logged for Palmbay Project
|  | % Defects in Technical docs | [5 empty] | % Defects in Coding
| Project 1 | Softheon | Project 2 | Project 3 | Project 4 | Project 5 | Galaxie Coffee | Project 1 | Project 2 | Project 3 | Project 4 | Project 5
DDD | 0.23 | 2 | 0.13 |  | 0.06 |  |  | 106 | 39 | 0 | 156
In Number | [7 empty] | 35.2159 | 12.9568 | 0 | 51.8272 | 0
D.3 % of Defects reported by client in the reporting period | [7 empty] | D.4 % DRE (DRE for the Reporting Period)
Formula: | (Total number of defects reported by Client in a project/Sum of all the defects reported by Clients in various projects) * 100 | [6 empty] | Formula: | (Internal QC Defects / (Internal + Customer Reported Defects))*100
Frequency: | Project Closure/ Periodically | [6 empty] | Frequency: | Periodically
Unit: | % | [6 empty] | Unit: | %
Condition: | No Defect log has been logged for Palmbay Project | [6 empty] | Goal: | 80
[8 empty] | Condition: | Only for projects reviewed or that which are in testing /UAT phase
| Project 1 | Softheon | Project 2 | Project 3 | Project 4 | Project 5 |  |  | Project 1 | Project 2 | Project 3 | Project 4 | Project 5
Defects(Client) | 27 | 2 | 7 | 0 | 9 | 0 |  | DRE(%) | 79.7 | 84.78 | 0 | 94.55
% Defects | 60 | 4.4444 | 15.5556 | 0 | 20 | 0
Above mentioned is dummy data
D.5 % of defects in technical docs till the reporting period
Formula: | (Total number of defects in technical docs till the reporting period / (total number of defects in technical docs + total number of defects in code) till the reporting period) * 100
Frequency: | Project Closure/ Periodically
Unit: | %
Condition: | No Defect log has been logged for Palmbay Project
% Defects in Technical docs
| Project 1 | Project 2 | Project 2 | Project 3 | Project 4 | Project 5
Defects | 0 | 2 | 0 | 0 | 0 | 0
% Defects | 0 | 100 | 0 | 0 | 0 | 0

## Project Effort Dist
Project Effort Distribution
|  | Dummy Data |  |  |  |  | Dummy Data
|  | Projects |  |  |  |  | Projects
|  | Project 1 | Project 2 | Project 3 | Project 4 | Project 5 | Project 1 | Project 2 | Project 3 | Project 4 | Project 5
Requirement Analysis | RA | 90 | 16 |  | 80 |  | 2.7439 | 2.2213 | 0 | 4.92 | 0 | 1.977
Design | DS | 85 | 10 |  | 120 | 0 | 2.5915 | 1.3883 | 0 | 7.3801 | 0 | 2.272
Coding | CD | 1450 | 352 | 2736 | 508 | 0 | 44.2073 | 48.8685 | 98.2053 | 31.2423 | 0 | 44.5047
Testing | TS | 389 | 96 | 0 | 180 | 0 | 11.8598 | 13.3278 | 0 | 11.0701 | 0 | 7.2515
Deployment | DP | 96 | 24 | 0 | 24 | 0 | 2.9268 | 3.3319 | 0 | 1.476 | 0 | 1.547
Documentation | DO | 186 | 33 | 0 | 68 | 9 | 5.6707 | 4.5814 | 0 | 4.182 | 100 | 22.8868
Technical Reviews & Meeting | TR | 166 | 43.3 | 0 | 73 | 0 | 5.061 | 6.0114 | 0 | 4.4895 | 0 | 3.1124
Change Request | CR | 678 | 62 | 0 | 438 | 0 | 20.6707 | 8.6075 | 0 | 26.9373 | 0 | 11.2431
Project Management | PM | 90 | 40 | 0 | 110 | 0 | 2.7439 | 5.5532 | 0 | 6.7651 | 0 | 3.0124
Configuration Management | CM | 50 | 16 | 0 | 25 | 0 | 1.5244 | 2.2213 | 0 | 1.5375 | 0 | 1.0566
Research & Development | RD | 0 | 28 | 50 | 0 | 0 | 0 | 3.8873 | 1.7947 | 0 | 0 | 1.1364
Total |  | 3280 | 720.3 | 2786 | 1626 | 9 | 100 | 100 | 100 | 100 | 100 | 100
534
Note on E6: Rahul: RA+SRS Review
Note on G6: Rahul: RA+SRS Review
Note on F8: Rahul: only estimated affort
Note on D10: Rahul: All release Demo+ UAT
Note on G10: Rahul: Here deployment is UAT
Note on D11: Rahul: Test Plan + Test Case 56+130
Note on E11: Rahul: Test Plan(8)+Test Case(40)+QA doc(4)
Note on G11: Rahul: Test Plan(8)+Test Case(60)
Note on D12: Rahul: TP (24)Review+TC Review(70)+Code Review(16)+ Design Review(56)
Note on E12: Rahul: Project meeting+internal meeting(25.3)+TP (3)Review+TC Review(8)+Code Review(1)+ Design Review(6)
Note on G12: Rahul: TP Review (12) +TC Review(24)+Code Review(13)+ Design Review(24)
Note on D13: Rahul: All affort count
Note on G13: Rahul: All affort count
Note on E16: Rahul: Req Dev 16+28

## Analysis Sheet
Metrics Report #
Action Plan:
Schedule Variance and Deliveries:-
1 | Effort Varience for Closed Project (EMP:RA) is high.
Defects:-
2 | Ratio of QC : Client defects is 100:0 , as the client reported bugs are not tracked in QC tracking sheet. No Defect log has been created for Galaxie Coffee Project in bugzilla hence data for the Galaxie Coffee Project is calculated from excel sheet.
HC and Training:-
3 | Trainings conducted during the last quarter was mostly on self learning and it is still in progress ,Training effectivness activity is not done properly. The Average traings conducted during the year should be 4 mandays/ person
Customer Satisfaction Survey:-
4 | Customer Satisfaction feedback forms are not recevied in the last Quarter