## Monthly ORG Quality Metrics 13
Schedule Variance | ((Actual effort in the project– initially planned effort for the project) / initially planned effort for the project) *100
|  | Project 1 | Project 2 | Project 3 |  | Project 4 | Project 5 | Project 6 | Project 7 | Total (%)
| Jan |  |  | 42.85 | [5 empty] | 42.85
| Feb | [8 empty] | 0
| March | [8 empty] | 0
| April | [8 empty] | 0
| May | [8 empty] | 0
| June | 0 | [7 empty] | 0
| July | 0 | 0 | [6 empty] | 0
| August | [5 empty] | -3.3333 |  |  | -3.3333
| September | [6 empty] | 207.1429 |  | 207.1429
| October | [8 empty] | 0
| November | 9.0909 | [7 empty] | 9.0909
| December | [7 empty] | -5.9603 | -5.9603
Effort Variance | ((Actual effort in the project– initially planned effort for the project) / initially planned effort for the project) *100
|  | Project 1 |  | Project 2 |  | Project 3 |  | Project 4 |  | Project 5 |  | Project 6 |  | Project 7 |  | EV in %
|  | P | A | P | A | P | A | P | A | P | A | P | A | Total Pl | Total Act
| Jan |  |  | 58 | 62 |  |  | 39 | 51 |  |  |  |  | 39 | 51 | 30.7692
| Feb | [6 empty] | 98 | 137 |  |  |  |  | 98 | 137 | 39.7959
| March | [6 empty] | 134 | 120 |  |  |  |  | 134 | 120 | -10.4478
| April | [12 empty] | 0 | 0 | #DIV/0!
| May | [12 empty] | 0 | 0 | #DIV/0!
| June | 2331 | 3466 |  |  |  |  | 1078 | 412 |  |  |  |  | 3409 | 3878 | 13.7577
| July |  |  |  |  | 664 | 532 | [6 empty] | 664 | 532 | -19.8795
| August | [12 empty] | 0 | 0 | #DIV/0!
| September | [6 empty] | 1316 | 584 | 510 | 552 |  |  | 1826 | 1136 | -37.7875
| October | [12 empty] | 0 | 0 | #DIV/0!
| November | 2649 | 2102 | [10 empty] | 2649 | 2102 | -20.6493
| December | [10 empty] | 2080 | 1354 | 2080 | 1354 | -34.9038
Defect Removal Effectiveness | (Internal QC Defects / (Internal + Customer Reported Defects))*100
|  | Project 1 | Project 2 | Project 3 |  | Project 4 | Project 5 | Project 6 | Project 7 | Total DRE
| Jan |  |  | 84.7826 |  | 100% |  |  |  | 85.7826
| Feb |  |  |  |  | 83.33% |  |  |  | 83.33%
| March |  |  |  |  | 100% |  |  |  | 100%
| April |  |  |  |  | 100% |  |  |  | 100%
| May |  |  |  |  | 100 |  |  |  | 100
| June | 93.83 |  |  |  | 98 |  |  |  | 191.83
| July |  | 84.62 |  |  | 94 |  |  |  | 178.62
| August |  |  |  |  | 95 | 100 |  |  | 195
| September |  |  |  |  | 100 |  |  |  | 100
| October |  |  |  |  | 82 |  |  |  | 82
| November | 93.55 |  |  |  | 83 |  |  |  | 176.55
| December | [7 empty] | 100 | 100
Total No. of Defect found Internal |  | Project 1 | Project 2 | Project 3 |  | Project 4 | Project 5 | Project 6 | Project 7 | Total defects
| Jan |  |  | 40 |  | 6 |  |  |  | 46
| Feb |  |  |  |  | 5 |  |  |  | 5
| Meach |  |  |  |  | 2 |  |  |  | 2
| April |  |  |  |  | 7 |  |  |  | 7
| May |  |  |  |  | 1 |  |  |  | 1
| June | 75 |  |  |  | 78 |  |  |  | 153
| July | 48 | 65 |  |  | 90 |  |  |  | 203
| August |  |  |  |  | 38 | 162 |  |  | 200
| September | 114 |  |  |  | 19 |  |  |  | 133
| October | 117 |  |  |  | 9 |  |  |  | 126
| November | 28 |  |  |  | 5 |  |  |  | 33
| December | [7 empty] | 215 | 215
Total No. of Defect found by client or external |  | Project 1 | Project 2 | Project 3 |  | Project 4 | Project 5 | Project 6 | Project 7 | Total defects
| Jan |  |  | 20 |  | 0 |  |  |  | 20
| Feb |  |  |  |  | 1 |  |  |  | 1
| March |  |  |  |  | 0 |  |  |  | 0
| April |  |  |  |  | 0 |  |  |  | 0
| May |  |  |  |  | 0 |  |  |  | 0
| June |  |  |  |  | 2 |  |  |  | 2
| July | 5 | 10 |  |  | 6 |  |  |  | 21
| August |  |  |  |  | 2 | 0 |  |  | 2
| September | 2 |  |  |  | 0 |  |  |  | 2
| October |  |  |  |  | 2 |  |  |  | 2
| November |  |  |  |  | 1 |  |  |  | 1
| December | [7 empty] | 0 | 0
Note on F3: Rahul: Approval of this CR came late and it should have been delivered on 25th Jan,13 (Friday) but Due to incorrect file format uploaded by the client take more time for troubleshooting to this error occurance. Hence it was delivered on 28th Jan,13(Monday)
Note on D54: Rahul: Come from "PalmBay_Test Execution Plan Progress Report_19072013"
Note on D55: Rahul: Come from "PalmBay_Test Execution Plan Progress Report_19072013"
Note on E55: Rahul: Come from "DEP_Test Execution Plan and Progress Report_25072013"
Note on D57: Rahul: Come from "PalmBay_Test Execution_Status Report_30Oct"
Note on D58: Rahul: Come from "PalmBay_Test Execution_Status Report_30Oct"
Note on D69: Rahul: Come from "PalmBay_Test Execution Plan Progress Report_19072013"
Note on E69: Rahul: Come from "DEP_Test Execution Plan and Progress Report_25072013"
Note on D71: Rahul: Come from "PalmBay_Test Execution_Status Report_30Oct"

## Monthly ORG Quality Metrics 14
Schedule Variance | ((Actual effort in the project– initially planned effort for the project) / initially planned effort for the project) *100
|  | Project 1 | Project 2 | Project 3 |  | Project 4 | Project 5 | Project 6 | Project 7 | Total (%)
| Jan | [8 empty] | 0
| Feb | [8 empty] | 0
| March | [8 empty] | 0
| April | [8 empty] | 0
| May | [8 empty] | 0
| June | [8 empty] | 0
| July | [8 empty] | 0
| August | [8 empty] | 0
| September | [8 empty] | 0
| October | [8 empty] | 0
| November | [8 empty] | 0
| December | [8 empty] | 0
Effort Variance | ((Actual effort in the project– initially planned effort for the project) / initially planned effort for the project) *100
|  | Project 1 |  | Project 2 |  | Project 3 |  | Project 4 |  | Project 5 |  | Project 6 |  | Project 7 |  | EV in %
|  | P | A | P | A | P | A | P | A | P | A | P | A | Total Pl | Total Act
| Jan | [12 empty] | 0 | 0 | #DIV/0!
| Feb | [12 empty] | 0 | 0 | #DIV/0!
| March | [12 empty] | 0 | 0 | #DIV/0!
| April | [12 empty] | 0 | 0 | #DIV/0!
| May | [12 empty] | 0 | 0 | #DIV/0!
| June | [12 empty] | 0 | 0 | #DIV/0!
| July | [12 empty] | 0 | 0 | #DIV/0!
| August | [12 empty] | 0 | 0 | #DIV/0!
| September | [12 empty] | 0 | 0 | #DIV/0!
| October | [12 empty] | 0 | 0 | #DIV/0!
| November | [12 empty] | 0 | 0 | #DIV/0!
| December | [12 empty] | 0 | 0 | #DIV/0!
Defect Removal Effectiveness | (Internal QC Defects / (Internal + Customer Reported Defects))*100
|  | Project 1 | Project 2 | Project 3 |  | Project 4 | Project 5 | Project 6 | Project 7 | Total DRE
| Jan | [8 empty] | 0
| Feb | [8 empty] | 0%
| March | [8 empty] | 0%
| April | [8 empty] | 0%
| May | [8 empty] | 0
| June | [8 empty] | 0
| July | [8 empty] | 0
| August | [8 empty] | 0
| September | [8 empty] | 0
| October | [8 empty] | 0
| November | [8 empty] | 0
| December | [8 empty] | 0
Total No. of Defect found Internal |  | Project 1 | Project 2 | Project 3 |  | Project 4 | Project 5 | Project 6 | Project 7 | Total defects
| Jan | [8 empty] | 0
| Feb | [8 empty] | 0
| Meach | [8 empty] | 0
| April | [8 empty] | 0
| May | [8 empty] | 0
| June | [8 empty] | 0
| July | [8 empty] | 0
| August | [8 empty] | 0
| September | [8 empty] | 0
| October | [8 empty] | 0
| November | [8 empty] | 0
| December | [8 empty] | 0
Total No. of Defect found by client or external |  | Project 1 | Project 2 | Project 3 |  | Project 4 | Project 5 | Project 6 | Project 7 | Total defects
| Jan | [8 empty] | 0
| Feb | [8 empty] | 0
| March | [8 empty] | 0
| April | [8 empty] | 0
| May | [8 empty] | 0
| June | [8 empty] | 0
| July | [8 empty] | 0
| August | [8 empty] | 0
| September | [8 empty] | 0
| October | [8 empty] | 0
| November | [8 empty] | 0
| December | [8 empty] | 0